## W1
PROJECT REPORT
Group | Caffein
Week | 17/02/2025 - 24/02/2025
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Coding new module | All member | Pending | Pending Table module because of final exam
2 | Review another member code | Le Dinh Khoi | In Progress
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
1 | Delay coding | All team member
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Coding new module | All team | 28/02/2025
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes