## W1
PROJECT REPORT
Group | Caffein
Week | 11/01/2025 - 18/01/2025
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Create Blackbox Testcase | All Team | Completed
2 | Review and update Blackbox TC | All Team | Completed
3 | Fix SRS | All Team | Completed
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
1
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Start coding module | All team | 24/01/2023
2 | Review and fix | All team | 24/01/2023
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes