## W1
PROJECT REPORT
Group | Caffein
Week | 03/03/2025 - 17/03/2025
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Implementation Export Revenue Features | KhoiLD | Completed | Export revenue to csv or excel
2 | Review teammate coding | KhoiLD
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
1 | Take time for resolve teammate commit | KhoiLD
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Support teammate for fixing bug | All team
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes