## W1
PROJECT REPORT
Group | Caffein
Week | 11/01/2025 - 18/01/2025
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Completed Database design | Khôi | Completed | Draw and check use case
2 | Completed Project plan | All Team | Completed | Completed project plan, create SRS
3 | Draw/design front end | All Team | Completed | Use tool (Draw.io, Balsamiq,...)
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
1
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
| Create Blackbox Testcase | All team | 24/01/2023 | Decide database type: SQL
| Review and update Blackbox TC | All team | 24/01/2023 | Meeting
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes