## W1
PROJECT REPORT
Group | Caffein
Week | 18/03/2025 - 25/03/2025
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Merge pull request for Order feature | TrieuLQ | Completed
2 | Coding CRUD Table Detail | TrieuLQ | In Progress
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Review Table Detail | All team | 24/3/2025
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes