## W5
PROJECT REPORT
Group | Caffein Management
Week | 24/02/2025 - 03/03/2025
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Coding second module(View Salary) | Thi | Pending
2 | Finish first module | Thi | Completed
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
1 | Delay second module(View Salary) | Thi | In Progress | Resolve issue with calculate salary, how to display to screen.
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Continue with second module | Thi | 2025-03-03 | Attempt to finish module
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes