## W1
PROJECT REPORT
Group | Caffeine Management
Week | 04/02/2025 - 08/02/2025
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Hoàn thành Black Box Test Case | All Team | Completed | Đã hoàn thành black box test case theo phần của em được chia bao gồm chức năng: CRUD promotion, Accept shift.
2
3
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
| Bắt đầu code phần CRUD promotion | All team | 18/02/2025
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes