## W1
PROJECT REPORT
Group | Caffein
Week | 26/03/2025 - 01/04/2025
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Complete CRUD Table Detail | TrieuLQ | Completed | None
2 | Test all function | All member | In Progress | None
3 | Review member's code | TrieuLQ | Completed | None
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
1 | Merge code | All member | In Progress | Too many commits when deadline is coming, there are some problems while merging code from members
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Prepare slide and product for presentation | All member | 2025-01-03 | None
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes