## W1
PROJECT REPORT
Group | Caffein
Week | 26/02/2025 - 01/03/2025
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Coding second module (customers order) | TrieuLQ | Pending
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
1 | Waiting for other member's coding (table module) | Khoi Le
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Complete second module | All team | 17/3/2025
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes