## W3
PROJECT REPORT
Group | Caffein
Week | 10/02/2025 - 17/02/2025
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Coding | All member | Completed | Implement Authorize + Authentication
2 | Modify database | All member | In Progress
3 | Review code | Le DInh Khoi | In Progress
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
| Coding missing and next section modules | All team | 19/02/2025
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes