## V1
Date | Duration (h) | Timeframe | Topic | Status | Member
2025-01-09 | 14 | 09:00-23:00 | Mock Project - Kick off + Create requirement outline + Project Plan | Done | All member
2025-01-10 | 14 | 09:00-23:00 | Mock Project - Create SRS | Done | All member
2025-01-15 | 14 | 09:00-23:00 | Mock Project - Review and update SRS | Done | All member
2025-01-17 | 14 | 09:00-23:00 | Mock Project - Database Design + Review Database Design |  | All member
2025-01-22 | 14 | 09:00-23:00 | Mock Project - Create Blackbox Testcase |  | All member
2025-01-24 | 14 | 09:00-23:00 | Mock Project - Review and update Blackbox TC |  | All member
off tet
2025-02-09 | 14 | 09:00-23:00 | Coding - Authenticate/Authorize |  | Khôi
|  |  | CRUD beverage |  | Hải
|  |  | CRUD staff |  | Triều
|  |  | CRUD promotion |  | Thi
|  |  | CRUD inventory |  | Huỳnh
2025-02-19 | 14 | 09:00-23:00 | Set table - Update table |  | Khôi
|  |  | Update profile |  | Hải
|  |  | Create bill |  | Triều
|  |  | Export inventory data |  | Huỳnh
|  |  | View revenue |  | Thi
2025-03-04 | 14 | 09:00-23:00 | View salary |  | Huỳnh
|  |  | Request shift |  | Hải
|  |  | Accept shift |  | Thi
|  |  | Export revenue report |  | All member
2025-03-11 | 14 | 09:00-23:00 | Mock Project - Review code + UT |  | All member
2025-03-16 | 14 | 09:00-23:00 | Mock Project - UT |  | All member
2025-03-21 | 14 | 09:00-23:00 | Mock Project - IT |  | All member
2025-03-24 | 14 | 09:00-23:00 | Mock Project - IT + Create Test Report |  | All member
2025-03-29 | 14 | 09:00-23:00 | Mock Project - Final Report
2025-03-30 | 14 | 09:00-23:00 | Mock Project - Final Report (cont)
Tên đề tài: | Xây dựng website quản lí quán cafe
Formulas:
Date = IF(WEEKDAY([Date, row above])=6,[Date, row above]+ 3,[Date, row above]+ 1)