## W6
PROJECT REPORT
Group | Caffein Management
Week | 03/03/2025 - 10/03/2025
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Coding second module(Profile) | Thi | In Progress
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
1 | Delay second module(Profile) | Thi | In Progress | Resolve issue with logic.
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Continue with second module | Thi | 14/3/2025 | Attempt to finish module
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes